## Sheet1
PROJECTMANAGEMENT | ASSIGNED TO | DURATIONS(WEEKS) | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9
PHASE 1
1.1 METHODOLOGY & SCOPE | PROJECT MANAGER | WEEK 1 | bar: WEEK 1
1.2 ROLE ALLOCATION | ALL MEMEBERS | WEEK 2 | bar: WEEK 1
1.3 PLAN SUBMISSION | REQUIREMENT LEAD | WEEK 2 | bar: WEEK 2
PHASE 2
2.1 STAKEHOLDER ELICITATION | REQUIREMENT LEAD | WEEK 3 | bar: WEEK 3
2.2 REQUIREMENTS SPECIFOCATIONS | REQUIREMENT LEAD | WEEK 4 | bar: WEEK 4
2.3 SRS SUBMISSION | TEST LEAD | WEEK 5 | bar: WEEK 5
PHASE 3
3.1 SYSTEM ARCHITECTURE DESIGN | DESIGN LEAD | WEEK 6 | bar: WEEK 6
3.2 DATABASE SCHEMA & ERD | DESIGN LEAD | WEEK 6 | bar: WEEK 6
3.3 CLASS DIAGRAM,UI MOCKUPS & SDD | DESIGN LEAD | WEEK 7 | bar: WEEK 7
PHASE 4
4.1 TECH STACK STEUP & ARCHITECTURE | IMPLEMENTATION LEAD | WEEK 7 | bar: WEEK 7
4.2 CORE BACKEND CODING | IMPLEMENTATION LEAD | WEEK 8
4.3 UI & SYSTEM INTEGRATION | ALL MEMEBERS | WEEK 8 | bar: WEEK 8
PHASE 5
5.1 UNIT & INTEGRATION CODING | TEST LEAD | WEEK 9 | bar: WEEK 8
5.2 TEST PLAN & CASES SUBMISSION | TEST LEAD | WEEK 9 | bar: WEEK 8
5.3 WORKING SYSTEM & VIVA PRESENTATION | ALL MEMBERS | WEEK 9 | bar: WEEK 9

## Gantt
PROJECT MANAGEMENT | Start Week | Duration | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9
1.1 Methodology & Scope | 1 | 1 | bar: W1
1.2 Role Allocation | 2 | 1 | bar: W2
1.3 Plan Submission | 3 | 1 | bar: W3
2.1 Stakeholder Elicitation | 4 | 1 | bar: W4
2.2 Requirements Specification | 4 | 1 | bar: W4
2.3 SRS Submission | 5 | 1 | bar: W5
3.1 System Architecture Design | 6 | 1 | bar: W6
3.2 Database Schema & ERD | 7 | 1 | bar: W7
3.3 Class Diagram/UI Mockups/SDD | 7 | 1 | bar: W7
4.1 Tech Stack Setup | 7 | 1 | bar: W7
4.2 Core Backend Coding | 8 | 1 | bar: W8
4.3 UI & System Integration | 8 | 1 | bar: W8
5.1 Unit & Integration Testing | 9 | 1 | bar: W9
5.2 Test Plan Submission | 9 | 1 | bar: W9
5.3 Working System & Viva | 9 | 1 | bar: W9